Guide 2. APT Project Development

Capstone Course

1. APT Project Progress Summary

Below you will find several fields that you must complete with the requested information.

| APT project progress summary | During this phase, the team completed the planning and design stage of the CowTracker project, a mobile and web livestock management application that identifies each animal through a QR code. The Project Charter, the WBS Matrix, the Gantt Chart and the budget were produced, and the requirements specification (SRS) was drawn up, with its spreadsheet of 25 functional and 13 non-functional requirements, the extended use cases and the system mockups. Based on these inputs, the System Architecture Document (SAD) was produced. It describes the context and purpose of the system, its architectural goals and constraints, the architecture views (4+1 approach) and the logical view, with the class and relational diagrams (33 tables) and a description of each one. With this, the objectives of the stage were met: defining the scope and requirements, planning time and costs, designing the interface, and establishing the architecture and data model of the system. |
| --- | --- |
| Objectives | General objective: to develop a mobile and web application that optimizes cattle management through the digitization of records, identification with QR codes and report generation, improving efficiency, health control and productivity on farms. Specific objectives: 1. Implement a QR code identification system for each bovine. 2. Digitize the recording and tracking of key events such as treatments, vaccinations, reproduction and diseases. 3. Automate alerts and reminders to optimize health control. 4. Incorporate milk production prediction using machine learning. 5. Manage commercialization: purchases from suppliers and sales of cattle and milk. |
| Methodology | To address the problem, a waterfall methodology will be used, adapted to the context of our project which has a duration of 3 months of work, considering iterations with incremental and functional deliveries, which allows validating progress frequently and adjusting the scope according to the results. The development will be organized in the following stages: - Analysis and requirements gathering: definition of roles, modules, and system workflows. - Design: modeling of the relational database and definition of the architecture (mobile app, web app, backends, and external services). - Development by modules: implementation of farms, livestock, veterinary, reproduction, production, catalogs, purchases/sales, and documents, prioritizing a minimum viable product. - Integration of external services: Webpay Plus and push notifications. - Testing and quality assurance: unit, integration, and e2e tests, plus typecheck and lint in each iteration. - Documentation and deployment: technical documentation and user guides |
| Evidence of progress | Evidence presented: CowTracker System Architecture Document (SAD), version 1.0, complemented by the Gantt Chart, the WBS Matrix and the SRS. How it shows progress: the SAD translates the SRS requirements into architectural decisions: it defines the quality goals (performance, security, offline operation, scalability), the project constraints and the class and relational models, with their primary and foreign keys. The Gantt Chart and the WBS Matrix support the planning of activities, deadlines and costs for this phase. Quality assurance: the institutional SAD template and the 4+1 views approach were used; traceability was maintained between requirements, use cases and architecture; and the data model was represented using the standard relational notation (PK, FK and data types), updating the diagrams every time the model changed. |
| 2. Work Plan Monitoring |
| Carefully examine your work plan, focusing especially on the progress status and adjustments columns. |

| Work Plan |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Competency or competency units | Activities | Resources | Activity duration | Responsible | Observations | Progress status | Adjustments |
| Manage IT projects, offering alternatives for decision-making according to the organization's requirements | Planning, agile management and monitoring of the CowTracker project | GitHub Projects / Jira / Plane, Kanban board, project management templates | 2 weeks (ongoing throughout the semester) | Lucas Melendez, Justin Serón, Danery Arriagada, Camilo Le Fort | Facilitating factor: Adoption of Scrum for incremental deliveries | In progress |  |
| Offer IT solution proposals by comprehensively analyzing processes according to the organization's requirements | Gathering and specification of livestock requirements | Google Docs, software specification template (SRS) | 2 weeks | Lucas Melendez, Justin Serón | Facilitating factor: Well-defined agricultural business rules. Difficulty: Accurately capturing the diversity of veterinary and production workflows | Completed |  |
| Build the architectural model of a systemic solution that supports business processes according to the organization's requirements and industry standards | Design of a decoupled architecture and containerized environment | Docker, Docker Compose, technical architecture documentation | 1 week | Camilo Le Fort, Danery Arriagada | Facilitating factor: Modern architecture based on microservices/decoupled APIs. Difficulty: Network coordination and synchronization between multiple local containers | Completed |  |
| Program queries or routines to manipulate information in a database according to the organization's requirements | Programming of data manipulation and persistence routines | Postgres, SQL scripts | 1 week | Lucas Melendez | Facilitating factor: Robust relational database. Difficulty: Optimizing queries on extensive animal histories | Completed |  |
| Develop the transformation of large volumes of data to obtain information and knowledge for the organization in order to support decision-making and the improvement of business processes, according to the organization's needs | Processing of production and reproduction data | Python, Postgres, processing scripts | 1.5 weeks | Justin Serón | Facilitating factor: Centralization of weighing, pregnancy and treatment events Difficulty: Consolidating metrics with incomplete data on large properties | In progress |  |
| Implement comprehensive systemic solutions to automate and optimize business processes according to the organization's needs | Integration of external services and payments | Webpay Plus, Banco Central, Chile Abierto, Open-Meteo and Firebase (FCM) APIs | 2 weeks | Danery Arriagada | Facilitating factor: Availability of free public APIs Difficulty: Dependence on third-party outages (mitigated with graceful degradation and caching) | Not started |  |
| Develop a software solution using techniques that allow the development and maintenance process to be systematized, ensuring the achievement of objectives | Development of web and mobile client applications | Expo, React Native, Next.js, Git | 3 weeks | Camilo Le Fort | Facilitating factor: Field usability adapted to mobile devices Difficulty: Maintaining functional parity and synchronization between the mobile and web apps | Not started |  |
| Resolve systemic vulnerabilities to ensure that the software built complies with the security standards required by the industry | Implementation of security, authentication and auditing | JWT, RBAC roles, audit log modules | 2 weeks | Justin Serón, Camilo Le Fort | Facilitating factor: Clear permission policies by role (admin, worker, veterinarian). Difficulty: Ensuring secure data isolation between different farms | Not started |  |

3. Adjustments Based on Monitoring

Delve deeper into the observations in your work plan. Analyze the planned activities and point out which aspects facilitated or hindered the execution of the plan. Explain how you addressed and/or will address the obstacles. Finally, indicate the adjustments you made to the work plan as a result of this analysis.

Factors that have facilitated and/or hindered the development of my work plan: Clear Definition of the Stack and Modular Architecture: The early decision to use a decoupled polyglot architecture made it possible to divide the work among the team members without the development of the Python analytics blocking the construction of the transactional base in Node.js Reuse of Contracts and the TypeScript Ecosystem: Using TypeScript in both the mobile application and the web platform made it possible to share data type definitions, speeding up interface design and preventing integration errors with the backend Early Containerization with Docker: Having the containers ready from the first weeks made it easier for the whole team to work on the same 33-table schema and seed data, eliminating discrepancies between local environments

Adjusted or eliminated activities: - Offline Module in the Mobile App (Adjusted): At first we thought that saving data without internet would be something simple that would take a couple of days, but when we tested it we realized that in the field the connection drops all the time, and records could be lost or duplicated if the app was closed. For that reason we decided to dedicate more time to it (two weeks instead of one) to build a well-made system that stores the data on the phone and sends it automatically once the signal returns, without duplicating animals or weigh-ins. - Push Notifications (Adjusted): We had planned to set up one notification system for phones and a separate one for the web. Since that would have taken us twice as long, we preferred to use a single Firebase solution for both platforms. This way we save code and keep everything centralized - Eliminated activities: We did not eliminate any functionality. The project's 25 requirements remain as they were planned from the beginning

Activities that have not started or are delayed: Activities not started: - General system testing: It is planned for the end of October, once we finish programming the main screens and functions. - Go-live and final delivery: This is the last stage and will take place during November. Are there delays in the project? We have no serious delays. We managed to recover time on the backend because we reused a lot of code across the cattle, farms and events screens. How will we ensure deadlines are met? - Instead of waiting until everything is finished before starting to test, we will test the modules that are already ready (such as login and cattle registration). - We will continue with short weekly coordination meetings to detect any problem in time (especially with the Webpay payment)

If the APT Project is a group project, in this column you must indicate the names of those responsible for each task or activity. This will later allow the evaluation to be differentiated for each member.